## Sheet2
Example 1 | Product Backlog is consistent i.e. It is stable
Points in the backlog | Points added | Points earned in the iteration / sprint | Cumulative points earned |  | Available Points | Percentage complete | Percentage Remaining (A) | Percentage Remaining (B) | Progress this month | total percentage complete
{{ is taken directly from the backlog, including completed work and remaining work. }} | {{Points added is equal to points in backlog this month less points in backlog last interation}} | {{ This is the total value of the story points earned this month}} | {{ This is the total of all story points earned to date, i.e. sum all previous points earned in month, including this month (Cumulative EV) }} |  | {{ Points in backlog now less all previously earned points, not including this month. We don’t subtract the points earned this month because they were still available at the start of the period. }} | This is equal to points earned in month divided by available points | Percent remaining last month less percent of backlog delivered this month. This is calculating how much work is remaining as a % of the total backlog. | Same stuff, different formula | Percentage of backlog completed this month multiplied by percent remaining. This is calculating the actual progress. It is weighting the calculated progress based on how much is to go. In the final period, the percent of backlog delivered this month is always 100%, because you have delivered all of what was left. Here we are working out what this month’s progress means for the entire project. For example if you had delivered 75% of the project, then you complete the project, the last sprint actually represent 25% of the project, even though it delivered 100% of what was in the backlog. | Percentage of backlog completed this month multiplied by percent remaining. This is calculating the actual progress. It is weighting the calculated progress based on how much is to go. In the final period, the percent of backlog delivered this month is always 100%, because you have delivered all of what was left. Here we are working out what this month’s progress means for the entire project. For example if you had delivered 75% of the project, then you complete the project, the last sprint actually represent 25% of the project, even though it delivered 100% of what was in the backlog.
|  |  |  | 0 | [5 empty] | 0
260 | 0 | 20 | 20 | 7.6923 | 260 | 7.6923 | 100 | 100 | 7.6923 | 7.6923
260 | 0 | 40 | 60 | 23.0769 | 240 | 16.6667 | 92.3077 | 92.3077 | 15.3846 | 23.0769
260 | 0 | 30 | 90 | 34.6154 | 200 | 15 | 76.9231 | 76.9231 | 11.5385 | 34.6154
260 | 0 | 10 | 100 | 38.4615 | 170 | 5.8824 | 65.3846 | 65.3846 | 3.8462 | 38.4615
260 | 0 | 40 | 140 | 53.8462 | 160 | 25 | 61.5385 | 61.5385 | 15.3846 | 53.8462
260 | 0 | 40 | 180 | 69.2308 | 120 | 33.3333 | 46.1538 | 46.1538 | 15.3846 | 69.2308
260 | 0 | 80 | 260 | 100 | 80 | 100 | 30.7692 | 30.7692 | 30.7692 | 100